## Dashboard
High
S.No | Description of Risk | Risk Level
10 | Risk-10 | High
7 | Risk-7 | High
4 | Risk-4 | High
1 | Risk-1 | High
0
0
0
0
0
0
Dashboard
Gantt
Resource
Timeline
Heatmap
Risks
Project Management Dashboard
Project Status
Total Task
72
Pending Task
In Progress Task
Completed Task
Top 10 Risk
Task not started even
after planned start date
46%
Task in Progress even
after planned end date
14%

## Gantt
1 | 0
| Task Name | Assigned to | Start Date | End Date | Status | Completion% | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30
| Task 1 | EMP-7 | 2019-01-01 | 2019-01-06 | Completed | 20% | 2019-01-01: Completed; 2019-01-02: Completed; 2019-01-03: Completed; 2019-01-04: Completed; 2019-01-05: Completed; 2019-01-06: Completed
| Task 2 | EMP-7 | 2019-01-04 | 2019-01-09 | Completed | 62% | 2019-01-04: Completed; 2019-01-05: Completed; 2019-01-06: Completed; 2019-01-07: Completed; 2019-01-08: Completed; 2019-01-09: Completed
| Task 3 | EMP-20 | 2019-01-07 | 2019-01-11 | Completed | 0% | 2019-01-07: Completed; 2019-01-08: Completed; 2019-01-09: Completed; 2019-01-10: Completed; 2019-01-11: Completed
| Task 4 | EMP-19 | 2019-01-10 | 2019-01-12 | In Progress | 42% | 2019-01-10: In Progress; 2019-01-11: In Progress; 2019-01-12: In Progress
| Task 5 | EMP-19 | 2019-01-11 | 2019-01-20 | Completed | 33% | 2019-01-11: Completed; 2019-01-12: Completed; 2019-01-13: Completed; 2019-01-14: Completed; 2019-01-15: Completed; 2019-01-16: Completed; 2019-01-17: Completed; 2019-01-18: Completed; 2019-01-19: Completed; 2019-01-20: Completed
| Task 6 | EMP-9 | 2019-01-21 | 2019-01-25 | Completed | 78% | 2019-01-21: Completed; 2019-01-22: Completed; 2019-01-23: Completed; 2019-01-24: Completed; 2019-01-25: Completed
| Task 7 | EMP-3 | 2019-01-24 | 2019-01-30 | Completed | 100% | 2019-01-24: Completed; 2019-01-25: Completed; 2019-01-26: Completed; 2019-01-27: Completed; 2019-01-28: Completed; 2019-01-29: Completed; 2019-01-30: Completed
| Task 8 | EMP-2 | 2019-01-30 | 2019-02-03 | Completed | 0% | 2019-01-30: Completed
| Task 9 | EMP-10 | 2019-02-08 | 2019-02-12 | Completed | 0%
| Task 10 | EMP-13 | 2019-02-10 | 2019-02-17 | Completed | 0%
| Task 11 | EMP-20 | 2019-02-16 | 2019-02-24 | In Progress | 100%
| Task 12 | EMP-1 | 2019-02-23 | 2019-03-05 | In Progress | 0%
| Task 13 | EMP-15 | 2019-03-06 | 2019-03-09 | In Progress | 0%
| Task 14 | EMP-3 | 2019-03-07 | 2019-03-12 | In Progress | 0%
| Task 15 | EMP-17 | 2019-03-13 | 2019-03-16 | In Progress | 100%
Dashboard
Gantt
Resource
Timeline
Heatmap
Risks
Inprogress
Completed
Pending
Weekend
Holiday
Gantt Chart

## Resource
1 | 0 | 2019-01-01
| Resource | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31
| EMP-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| EMP-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| EMP-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-7 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EMP-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dashboard
Gantt
Resource
Timeline
Heatmap
Risks
1 Task
No Task
> 1 Task
Weekend
Holiday
Resource Utilization

## Timeline
Dashboard
Gantt
Resource
Timeline
Heatmap
Risks
Project Timelines
Use scroll to change date

## Heat Map
0 | 2019 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2
| 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2
| 4 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1
| 5 | 2 | 0 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1
| 6 | 2 | 0 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 7 | 2 | 0 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1
| 8 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2
| 9 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
| 10 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
| 11 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2
| 12 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 2 | 1
| 13 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| 14 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 1
| 15 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1
| 16 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1
| 17 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| 18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
| 19 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 2
| 20 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 1
| 21 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1
| 22 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| 23 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 24 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| 25 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1
| 26 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1
| 29 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1
| 30 | 2 | 0 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2
| 31 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 2
Weekend
Holiday
Min
Max
Yearly Task Heatmap
Dashboard
Gantt
Resource
Timeline
Heatmap
Risks
Heat Map

## Risk
S.No | Description of Risk | Impact | Risk Level | Risk Owner | Notes
1 | Risk-1 | Impact -1 | High | EMP-6 | Put your notes here
2 | Risk-2 | Impact -2 | Medium | EMP-19 | Put your notes here
3 | Risk-3 | Impact -3 | Low | EMP-20 | Put your notes here
4 | Risk-4 | Impact -4 | High | EMP-18 | Put your notes here
5 | Risk-5 | Impact -5 | Medium | EMP-20 | Put your notes here
6 | Risk-6 | Impact -6 | Low | EMP-9 | Put your notes here
7 | Risk-7 | Impact -7 | High | EMP-16 | Put your notes here
8 | Risk-8 | Impact -8 | Medium | EMP-14 | Put your notes here
9 | Risk-9 | Impact -9 | Low | EMP-19 | Put your notes here
10 | Risk-10 | Impact -10 | High | EMP-15 | Put your notes here
Dashboard
Gantt
Resource
Timeline
Heatmap
Risks
Risk and Issues

## Data (hidden)
Task Name | Assigned to | Assigned to -2 | Assigned to -3 | Assigned to -4 | Start Date | End Date | Status | Completion% | Task Status
Task 1 | EMP-7 |  |  |  | 2019-01-01 | 2019-01-06 | Completed | 20% | G
Task 2 | EMP-7 |  |  |  | 2019-01-04 | 2019-01-09 | Completed | 62% | G
Task 3 | EMP-20 |  |  |  | 2019-01-07 | 2019-01-11 | Completed | 0% | G
Task 4 | EMP-19 |  |  |  | 2019-01-10 | 2019-01-12 | In Progress | 42% | A
Task 5 | EMP-19 |  |  |  | 2019-01-11 | 2019-01-20 | Completed | 33% | G
Task 6 | EMP-9 |  |  |  | 2019-01-21 | 2019-01-25 | Completed | 78% | G
Task 7 | EMP-3 |  |  |  | 2019-01-24 | 2019-01-30 | Completed | 100% | G
Task 8 | EMP-2 |  |  |  | 2019-01-30 | 2019-02-03 | Completed | 0% | G
Task 9 | EMP-10 |  |  |  | 2019-02-08 | 2019-02-12 | Completed | 0% | G
Task 10 | EMP-13 |  |  |  | 2019-02-10 | 2019-02-17 | Completed | 0% | G
Task 11 | EMP-20 |  |  |  | 2019-02-16 | 2019-02-24 | In Progress | 100% | A
Task 12 | EMP-1 |  |  |  | 2019-02-23 | 2019-03-05 | In Progress | 0% | A
Task 13 | EMP-15 |  |  |  | 2019-03-06 | 2019-03-09 | In Progress | 0% | A
Task 14 | EMP-3 |  |  |  | 2019-03-07 | 2019-03-12 | In Progress | 0% | A
Task 15 | EMP-17 |  |  |  | 2019-03-13 | 2019-03-16 | In Progress | 100% | A
Task 16 | EMP-6 |  |  |  | 2019-03-15 | 2019-03-23 | In Progress | 100% | A
Task 17 | EMP-6 |  |  |  | 2019-03-22 | 2019-03-26 | In Progress | 58% | A
Task 18 | EMP-18 |  |  |  | 2019-03-26 | 2019-03-30 | In Progress | 30% | A
Task 19 | EMP-6 |  |  |  | 2019-03-30 | 2019-04-07 | In Progress | 0% | A
Task 20 | EMP-3 |  |  |  | 2019-04-05 | 2019-04-08 | Completed | 0% | G
Task 21 | EMP-10 |  |  |  | 2019-04-07 | 2019-04-14 | Completed | 100% | G
Task 22 | EMP-11 |  |  |  | 2019-04-15 | 2019-04-22 | Pending | 0% | R
Task 23 | EMP-14 |  |  |  | 2019-04-21 | 2019-04-24 | Pending | 69% | R
Task 24 | EMP-8 |  |  |  | 2019-04-23 | 2019-04-25 | Pending | 100% | R
Task 25 | EMP-12 |  |  |  | 2019-04-24 | 2019-05-01 | Pending | 28% | R
Task 26 | EMP-12 |  |  |  | 2019-04-30 | 2019-05-06 | Pending | 42% | R
Task 27 | EMP-4 |  |  |  | 2019-05-06 | 2019-05-12 | Pending | 0% | R
Task 28 | EMP-6 |  |  |  | 2019-05-11 | 2019-05-14 | Pending | 77% | R
Task 29 | EMP-16 |  |  |  | 2019-05-13 | 2019-05-23 | Pending | 0% | R
Task 30 | EMP-20 |  |  |  | 2019-05-24 | 2019-05-30 | Pending | 100% | R
Task 31 | EMP-20 |  |  |  | 2019-05-30 | 2019-06-02 | Pending | 100% | R
Task 32 | EMP-3 |  |  |  | 2019-06-02 | 2019-06-12 | Pending | 100% | R
Task 33 | EMP-1 |  |  |  | 2019-06-12 | 2019-06-21 | Pending | 46% | R
Task 34 | EMP-19 |  |  |  | 2019-06-20 | 2019-06-23 | Pending | 0% | R
Task 35 | EMP-5 |  |  |  | 2019-06-24 | 2019-06-30 | Pending | 0% | R
Task 36 | EMP-20 |  |  |  | 2019-07-01 | 2019-07-05 | Pending | 27% | R
Task 37 | EMP-5 |  |  |  | 2019-07-03 | 2019-07-09 | Pending | 0% | R
Task 38 | EMP-2 |  |  |  | 2019-07-10 | 2019-07-12 | Pending | 0% | R
Task 39 | EMP-18 |  |  |  | 2019-07-11 | 2019-07-13 | Pending | 72% | R
Task 40 | EMP-17 |  |  |  | 2019-07-11 | 2019-07-18 | Pending | 0% | R
Task 41 | EMP-13 |  |  |  | 2019-07-16 | 2019-07-26 | Pending | 100% | R
Task 42 | EMP-5 |  |  |  | 2019-07-27 | 2019-08-04 | Pending | 72% | R
Task 43 | EMP-20 |  |  |  | 2019-08-04 | 2019-08-07 | Pending | 29% | R
Task 44 | EMP-16 |  |  |  | 2019-08-07 | 2019-08-12 | Pending | 0% | R
Task 45 | EMP-15 |  |  |  | 2019-08-12 | 2019-08-19 | Pending | 85% | R
Task 46 | EMP-5 |  |  |  | 2019-08-20 | 2019-08-26 | Pending | 100% | R
Task 47 | EMP-20 |  |  |  | 2019-08-27 | 2019-09-05 | Pending | 100% | R
Task 48 | EMP-12 |  |  |  | 2019-09-05 | 2019-09-11 | Pending | 0% | R
Task 49 | EMP-2 |  |  |  | 2019-09-12 | 2019-09-16 | Pending | 65% | R
Task 50 | EMP-9 |  |  |  | 2019-09-14 | 2019-09-22 | Pending | 100% | R
Task 51 | EMP-8 |  |  |  | 2019-09-20 | 2019-09-29 | Pending | 0% | R
Task 52 | EMP-1 |  |  |  | 2019-09-28 | 2019-09-30 | Pending | 71% | R
Task 53 | EMP-2 |  |  |  | 2019-09-29 | 2019-10-04 | Pending | 44% | R
Task 54 | EMP-15 |  |  |  | 2019-10-04 | 2019-10-08 | Pending | 100% | R
Task 55 | EMP-20 |  |  |  | 2019-10-08 | 2019-10-14 | Pending | 0%
Task 56 | EMP-12 |  |  |  | 2019-10-14 | 2019-10-16 | Pending | 100%
Task 57 | EMP-1 |  |  |  | 2019-10-14 | 2019-10-19 | Pending | 61%
Task 58 | EMP-15 |  |  |  | 2019-10-19 | 2019-10-25 | Pending | 100%
Task 59 | EMP-2 |  |  |  | 2019-10-25 | 2019-11-04 | Pending | 0%
Task 60 | EMP-13 |  |  |  | 2019-11-02 | 2019-11-12 | Pending | 100%
Task 61 | EMP-17 |  |  |  | 2019-11-10 | 2019-11-13 | Pending | 100%
Task 62 | EMP-4 |  |  |  | 2019-11-14 | 2019-11-20 | Pending | 59%
Task 63 | EMP-3 |  |  |  | 2019-11-20 | 2019-11-22 | Pending | 74%
Task 64 | EMP-10 |  |  |  | 2019-11-23 | 2019-12-03 | Pending | 0%
Task 65 | EMP-2 |  |  |  | 2019-12-02 | 2019-12-09 | Pending | 100%
Task 66 | EMP-12 |  |  |  | 2019-12-08 | 2019-12-11 | Pending | 61%
Task 67 | EMP-20 |  |  |  | 2019-12-09 | 2019-12-19 | Pending | 53%
Task 68 | EMP-7 |  |  |  | 2019-12-19 | 2019-12-24 | Pending | 0%
Task 69 | EMP-15 |  |  |  | 2019-12-24 | 2019-12-31 | Pending | 46%
Task 70 | EMP-6 |  |  |  | 2019-12-30 | 2020-01-04 | Pending | 0%
Task 71 | EMP-20 |  |  |  | 2020-01-05 | 2020-01-11 | Pending | 100%
Task 72 | EMP-19 |  |  |  | 2020-01-12 | 2020-01-20 | Pending | 0%
Formulas:
Task Status = IF([Status]="Completed","G",IF([Status]="In Progress",IF(TODAY()>[End Date],"A","G"),IF([Status]="Pending",IF(TODAY()>[Start Date],"R",""),"")))

## Settings (hidden)
Day | Holiday | Holiday | Date | Resource | Status
Sun | Y | Diwali | 2019-10-28 | EMP-1 | Completed
Mon | N | Christmas | 2019-12-15 | EMP-2 | Pending
Tue | N |  | 2019-01-10 | EMP-3 | In Progress
Wed | N |  | 2019-02-04 | EMP-4
Thu | N |  |  | EMP-5
Fri | N |  |  | EMP-6
Sat | Y |  |  | EMP-7
EMP-8
EMP-9
EMP-10
EMP-11
EMP-12
EMP-13
EMP-14
EMP-15
EMP-16
EMP-17
EMP-18
EMP-19
EMP-20

## Support (hidden)
84 | Time Line Chart | [5 empty] | Risk and issue
Start Date | Task | Status | Pending | In Progress | Completed | Total
2019-03-26 | Task 18 | In Progress | 0 | 2 | 0 | 2 | Total | 10 | Total 10
2019-03-27 |  |  | 0 | 0 | 0 | 0 | High | 4 | 40%
2019-03-28 |  |  | 0 | 0 | 0 | 0 | Medium | 3 | 30%
2019-03-29 |  |  | 0 | 0 | 0 | 0 | Low | 3 | 30%
2019-03-30 | Task 19 | In Progress | 0 | 2 | 0 | 2
2019-03-31 |  |  | 0 | 0 | 0 | 0
2019-04-01 |  |  | 0 | 0 | 0 | 0
2019-04-02 |  |  | 0 | 0 | 0 | 0 | Task
2019-04-03 |  |  | 0 | 0 | 0 | 0 | Total | 72 | Total 72
2019-04-04 |  |  | 0 | 0 | 0 | 0 | Pending | 51 | 70.83% | 29.17%
2019-04-05 | Task 20 | Completed | 0 | 0 | 2 | 2 | In Progress | 10 | 13.89% | 86.11%
2019-04-06 |  |  | 0 | 0 | 0 | 0 | Completed | 11 | 15.28% | 84.72%
2019-04-07 | Task 21 | Completed | 0 | 0 | 2 | 2
2019-04-08 |  |  | 0 | 0 | 0 | 0
2019-04-09 |  |  | 0 | 0 | 0 | 0 | Project Status | R
2019-04-10 |  |  | 0 | 0 | 0 | 0 | Task not started even after plan start date | 33 | 45.83%
2019-04-11 |  |  | 0 | 0 | 0 | 0 | In Progress even after end date | 10 | 13.89%
2019-04-12 |  |  | 0 | 0 | 0 | 0
2019-04-13 |  |  | 0 | 0 | 0 | 0
2019-04-14 |  |  | 0 | 0 | 0 | 0
2019-04-15 | Task 22 | Pending | 2 | 0 | 0 | 2 |  | R
2019-04-16 |  |  | 0 | 0 | 0 | 0
2019-04-17 |  |  | 0 | 0 | 0 | 0
2019-04-18 |  |  | 0 | 0 | 0 | 0
2019-04-19 |  |  | 0 | 0 | 0 | 0
2019-04-20 |  |  | 0 | 0 | 0 | 0
2019-04-21 | Task 23 | Pending | 2 | 0 | 0 | 2
2019-04-22 |  |  | 0 | 0 | 0 | 0
2019-04-23 | Task 24 | Pending | 2 | 0 | 0 | 2
2019-04-24 | Task 25 | Pending | 1 | 0 | 0 | 1
Formulas:
Start Date = [Start Date, row above]+1